## Contract Legal Terms
THE 5 DESIGNS
WORK CONTRACT STANDARD TERMS & CONDITIONS
Clause No. | Clause Heading | Agreement Terms & Execution Specifications
1.0 | Scope of Works | The scope of works is bounded strictly by the Bill of Quantities (BOQ) and authorized GFC drawings. Any variations, revisions, or additions requested verbally by the Client or Contractor will only be binding once processed and signed via a Joint Measurement Certificate (JMC) and a formal written Variation Order (VO) stating rates and impact on the timeline.
2.0 | Measurement & Billing | All progress bills raised by contractors and invoices raised to the client shall be measured jointly on-site based on actual net executed quantities. The billing calculations will strictly follow the measurement principles detailed in the JMC sheet (using Length x Width x Depth multipliers). Deductions for cut-outs and voids larger than 4 Sft will be enforced.
3.0 | Delay Penalties | Time is of the essence for this contract. If the Service Provider / Contractor fails to achieve the milestones outlined in the Project Timeline sheet due to reasons solely attributable to them, a delay penalty (Liquidated Damages) of 0.5% of the total pending work value per week of delay shall be levied, up to a maximum cap of 5% of the total contract value.
4.0 | Quality & Defect Liability | The Contractor guarantees that all materials and workmanship supplied match the standards outlined in the Vendor Scope of Work. A Defect Liability Period (DLP) of 12 (Twelve) calendar months from the date of final handover is applicable. Any structural defects, alignments issues, paint peeling, or hardware malfunction during this period shall be rectified by the Contractor at zero cost to the Client.
5.0 | Dispute Resolution | All disputes, claims, or differences arising out of or in connection with this work contract shall first be attempted to be resolved amicably through mediation between the Lead Designer, Contractor, and Client within 15 days. If unresolved, disputes shall be referred to arbitration under the Arbitration and Conciliation Act, 1996.
6.0 | Judicial Jurisdiction | This Contract is governed by and shall be construed in accordance with the laws of India. All legal actions, litigation, or judicial proceedings arising out of or related to this project, including claims on billing, measurements, or breaches, shall be subject to the exclusive jurisdiction of the competent courts located in Hyderabad, Telangana, India.