## Roomwise Checklist
THE 5 DESIGNS
ROOMWISE QUALITY CONTROL CHECKLIST
Done (TRUE/FALSE) | Room / Space | Structure Section | Checklist Pointer / Task | Assigned Contractor | Start Date | End Date | QC Status | QC Remarks
LIVING ROOM
↳ CEILING
FALSE | Living Room | Ceiling | Check layout alignment of GI framing suspension | Ceiling Specialist | 2026-08-11 | 2026-08-13 | Approved | Aligned as per drawings
FALSE | Living Room | Ceiling | Confirm conduit placement for magnetic track lights | Electrical Contractor | 2026-08-12 | 2026-08-14 | Approved | Wires checked & tagged
FALSE | Living Room | Ceiling | Verify gypsum board fixing, jointing & plaster tape | Ceiling Specialist | 2026-08-15 | 2026-08-18 | Pending | Taping completed
↳ FLOORING
FALSE | Living Room | Flooring | Subfloor cleaning and dual-layer waterproofing IPS | Civil Contractor | 2026-08-18 | 2026-08-20 | Approved | Pond test successful
FALSE | Living Room | Flooring | Dry layout review of Italian marble slabs (vein matching) | Stone Mason | 2026-08-21 | 2026-08-23 | Rework Required | Re-align slab #4 & #5
FALSE | Living Room | Flooring | Final marble laying, grouting and epoxy sealing | Stone Mason | 2026-08-24 | 2026-08-30 | Not Started | -
↳ ELEVATION NORTH
FALSE | Living Room | Elevation North | Plywood framework marking & HDHMR support backing | Carpentry Team | 2026-09-01 | 2026-09-03 | Pending | Ready for veneer
FALSE | Living Room | Elevation North | walnut veneer pasting & SS gold inlay groove fixing | Carpentry Team | 2026-09-04 | 2026-09-08 | Not Started | -
↳ ELEVATION SOUTH
FALSE | Living Room | Elevation South | Putty coats application & micro-cement base prep | Painting Team | 2026-09-09 | 2026-09-11 | Not Started | -
↳ ELEVATION EAST
FALSE | Living Room | Elevation East | Wiring conduits and boxes for TV console backboard | Electrical Contractor | 2026-09-02 | 2026-09-03 | Approved | Wires labeled
↳ ELEVATION WEST
FALSE | Living Room | Elevation West | Wall putty, base primer & texture paint finish | Painting Team | 2026-09-12 | 2026-09-15 | Not Started | -
MASTER BEDROOM
↳ CEILING
FALSE | Master Bed | Ceiling | G.I. ceiling frame suspension & level check | Ceiling Specialist | 2026-08-12 | 2026-08-14 | Pending | -
↳ FLOORING
FALSE | Master Bed | Flooring | Wooden flooring underlay installation | Flooring Contractor | 2026-08-26 | 2026-08-28 | Not Started | -