## Project Timeline
THE 5 DESIGNS
PHASE-BASED PROJECT TIMELINE & MATERIAL COMMITMENTS
Project: Luxury Residence |  |  | Lead Designer: Rahul S. |  |  | Client: Kapoor Residence |  |  | Duration: 12 Weeks |  |  | Start: 2026-07-01 |  |  | End: 2026-09-22 |  |  | Status: Scheduled
WBS No | Phase / Sub-Phase / Work Task | Responsible Party | Dependencies (Client/Team) | Sourcing Material Commitment | Start Date | End Date | Duration (Days) | Status | Progress (%) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1.0 | PHASE 1: DESIGN & APPROVALS |  |  |  | 2026-07-01 | 2026-07-15 | 14 | In Progress | 0.6
1.1 | Sub-Phase: 3D Layout & Space Planning | Designer | Client brief approved | N/A | 2026-07-01 | 2026-07-08 | 7 | Completed | 1 | bar: W1
1.2 | Sub-Phase: Material Specifications Selection | Sourcing Team | Client 3D sign-off | Marble catalogs, sample boards | 2026-07-09 | 2026-07-15 | 6 | In Progress | 0.3
2.0 | PHASE 2: CIVIL, WATERPROOFING & MEP SERVICES |  |  |  | 2026-07-16 | 2026-08-10 | 25 | Not Started | 0
2.1 | Sub-Phase: Civil Demolition & Layout Marking | Civil Cont. | Society NOC & layout finalization | N/A | 2026-07-16 | 2026-07-22 | 7 | Not Started | 0
2.2 | Sub-Phase: Plumbing & Electrical Rough-Ins | MEP Specialist | Civil layouts completed | Pipes & FR Cables committed: 2026-07-20 | 2026-07-23 | 2026-08-02 | 10 | Not Started | 0 | bar: Start: 2026-07-01 W4 to Start: 2026-07-01 W5
2.3 | Sub-Phase: Waterproofing & Floor IPS Leveling | Civil Cont. | Plumbing testing completed | Chemical base supply committed: 2026-07-22 | 2026-08-03 | 2026-08-10 | 7 | Not Started | 0
3.0 | PHASE 3: CEILING, JOINERY & SURFACE FINISHES |  |  |  | 2026-08-11 | 2026-09-22 | 42 | Not Started | 0
3.1 | Sub-Phase: Gypsum False Ceiling Suspension | Ceiling Cont. | MEP conduit check completed | Saint Gobain Gypsum committed: 2026-08-08 | 2026-08-11 | 2026-08-20 | 9 | Not Started | 0
3.2 | Sub-Phase: Wardrobes & Wall Paneling Carcass | Carpenters | Civil curing & ceilings complete | Greenply MR Plywood committed: 2026-08-15 | 2026-08-21 | 2026-09-08 | 18 | Not Started | 0 | bar: End: 2026-09-22 W8 to Status: Scheduled W10
3.3 | Sub-Phase: Wall Primer, Putty & Veneer Polish | Painting Team | Carpentry carcass finished | Paints & Melamine committed: 2026-09-05 | 2026-09-09 | 2026-09-18 | 9 | Not Started | 0
3.4 | Sub-Phase: Electrical Fixtures & Handover | PM / Sourcing | Final paint coats completed | COB lights & switches committed: 2026-09-10 | 2026-09-19 | 2026-09-22 | 4 | Not Started | 0 | bar: Status: Scheduled W12